## Sheet1
Date | Saurabh Mehra | Mansi Verma | Vikas Pandey | Shivam Singh | Overall Status
| Completed Design | Completed Design | Completed Design | Completed Design | Work Flow and design of project is ready
2020-02-11 | Member Portal | Subscription Microservice | Drugs Microservice | Refill Microservice
Authentication Service
Sequence Diagram
Date | Saurabh Mehra | Mansi Verma | Vikas Pandey | Shivam Singh | Overall Status
| Completed Member Portal | completed Subscription service | working on Drug MicroService | working on Refill Microservice | services are completed almost
2020-03-11 | Completed Authorization API | swagger Implemented | swagger Implemented | swagger Implemented | Integration with other services will
| Swagger Implemented |  |  |  | be completed by tommorow
Date | Saurabh Mehra | Mansi Verma | Vikas Pandey | Shivam Singh | Overall Status
| working on Integration part | working on Autherization | working on Autherization | working on Autherization | All services are completed
2020-04-11 |  | working on Integration | working on Integration | Working on Integration | reviewing Integration parts
Date | Saurabh Mehra | Mansi Verma | Vikas Pandey | Shivam Singh | Overall Status
2020-05-11 | Completed | Completed | Completed | Completed | Design and Coding is Completed
Working on Unit Testing
Date | Saurabh Mehra | Mansi Verma | Vikas Pandey | Shivam Singh | Overall Status
2020-06-11 | Completed | Completed | Completed | Completed | Design and Coding is Completed
Nunit Testing Completed
Date | Saurabh Mehra | Mansi Verma | Vikas Pandey | Shivam Singh | Overall Status
2020-07-11 | working On Cloud Deployment | working On Cloud Deployment | working On Cloud Deployment | working On Cloud Deployment | Design and Coding is Completed
Nunit Testing Completed
working On Cloud Deployment
Date | Saurabh Mehra | Mansi Verma | Vikas Pandey | Shivam Singh | Overall Status
2020-09-11 | working On Cloud Deployment | working On Cloud Deployment | working On Cloud Deployment | working On Cloud Deployment | Design and Coding is Completed
Nunit Testing Completed
working On Cloud Deployment
Date | Saurabh Mehra | Mansi Verma | Vikas Pandey | Shivam Singh | Overall Status
2020-10-11 | Completed | Completed | Completed | working | Cloud Deployment Almost Completed
Date | Saurabh Mehra | Mansi Verma | Vikas Pandey | Shivam Singh | Overall Status
2020-11-11 | Completed | Completed | Completed | Completed | Completed